HAITIAN RECONSTRUCTION FUND

NARRATIVE progress report

REPORTING PERIOD: july-december 2020

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Strengthening the Management of Services and the Health System in Haiti Programme Number (if applicable) 00098088 MPTF Office Project Reference Number: |  | Country/Region Haiti / Port-au-Prince |
|  |  | The purpose of this project is to improve the health conditions of the Haitian population having access to the network of health services implemented through two strategic priorities directly related to the priorities of the government. |
| Participating Organization(s) |  | Implementing Partners |
| Organizations that have received direct funding from the MPTF Office under this programme UNDP |  | National counterparts (government, private, NGOs & others) and other International Organizations UNDP Brazil |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: USD 19.800.000,00 MPTF /JP Contribution: by Agency (if applicable) |  |  | Overall Duration (months) 36 months |  |
| Agency Contribution by Agency (if applicable) |  |  | Start Date 23/06/2017 |  |
| Government Contribution (if applicable) |  |  | Original End Date 22/06/2020 |  |
| Other Contributions (donors) (if applicable) |  |  | Current End date 31/12/2020 |  |
| TOTAL: USD 19.800.000,00 |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes X No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes X No Date: dd.mm.yyyy |  | Name: Maria Teresa Amaral Fontes Title: Programme Analyst Participating Organization (Lead): UNDP Email address: maria.teresa.fontes@undp.org |

NARRATIVE REPORT FORMAT

# EXECUTIVE SUMMARY

This report describes the main results achieved under Project BRA/17/018 until December 2020.

# Purpose

Haiti is the poorest country in the Americas and its perverse indicators of health, specially life expectancy and infant mortality rate, reflect that serious problems still plague the health sector, such as:

- Low reception capacity of the existing health services;

- Low sanitary coverage characterized by a lack of sanitary facilities in comparison with the size of the population;

- Lack of equipment in many health institutions;

- Lack of infrastructure to accommodate the few existing equipment.

Although the right to health is a fundamental right that the Government of Haiti (GoH), through its Ministry of Public Health and Population of Haiti (MSPP), must ensure, the well-being of the population is dependent on improvements in the health service. Aware of this reality and faithful to its mission, the MSPP sought the financial support of the Haiti Reconstruction Fund (HRF) to promote the capacity of health management in the country.

This project gives continuity to NIM Project BRA/10/005, known as Tripartite Cooperation, a cooperation in health in Haiti under the Brazil-Cuba-Haiti Tripartite Memorandum of Understanding, signed in 2010 and implemented directly by UNDP Brazil with resources from the Government of Brazil (GoB). Project BRA/10/005 resulted a very successful experience of South-South Cooperation, promoting the strengthening of the health authority in Haiti and providing the country with three full equipped community reference hospitals, a rehabilitation center and one prosthesis and orthoses lab.

Project BRA/17/018 was designed around two strategic outcomes, in accordance with the guidelines of the Action Plan for the Recovery of Haiti (PARDH), especially with reference to its Pillar 3: social reconstruction; and program 3.3: increase access to health services. The outcomes ate: 1: Strengthening management, services, and governance in public health in Haiti; 2: Development and implementation of a plan for the management of the Tripartite Cooperation health services, with the aim of enabling sustainability and preservation of structures by the Haitian government.

Activities foreseen in the project are acquisition of strategic health products, professional training and strengthening primary health care and emergency services in Haiti. It also envisions the transfer of full management of the maintenance of health services built by Brazil in its previous cooperation to the responsibility of the MSPP. The actions to be performed are based on cross-sectional values that govern the South-South Cooperation and provide the key elements to improve the access to and quality of care in the health services network and, in the end, have an impact on the entire health system of Haiti.

# Results

Projects’ Initial Revision was signed on August 3rd, 2017. Aiming to attend the MSPP demands, UNDP Brazil was expected to conduct several activities in a quick manner, such as: organizing field missions, hiring project team, designing a detailed workplan with experts from MSPP and UNOPS Haiti, among others.

- Narrative reporting on results:

- Outcomes:

The purpose of Project BRA/17/018 is to improve the health conditions of the Haitian population having access to the network of health services. As described above, the main outcomes of the project are:

- Strategic Axis 1: Strengthening of management, services, and governance in public health in Haiti;

- Strategic Axis 2: Development and implementation of a plan for the gradual transfer of the Tripartite Cooperation health services management in order to enable sustainability and preservation of structures by the Haitian government.

As stated in the Project Document, UNOPS Haiti (UNOPS) was selected as an implementing partner. Results of the previous cooperation were held as very satisfactory and for that, UNOPS was invited by GoB and UNDP to give continuity to the services also under Project BRA/17/018. For the achievement of the listed outcomes for Project BRA/17/018, an UN to UN Agreement was signed in 2017 with UNOPS in order to optimize the operations of the health facilities (3 HCRs and 1 IHR) and assets; to establish sustainable capacities within the MSPP maintenance units; to guarantee the offer of medical services to the local population; and to implement a progressive handover plan so that the hospitals and a rehabilitation center become under the MSPP full control and financial support.

Similarly, the partnership with PAHO/WHO was also foreseen in the scope of the Project and an UN to UN Agreement was signed with the agency in August 2019. Through this collaborative agreement, PAHO/WHO was expected to provide capacity-building and technical support to health managers, professionals and technicians of the MSPP in Haiti to improve the management of medical and health emergencies in three hospitals, while ensuring the continuity of health care services through the strengthening and expansion of the community health model.

Main activities of the signed Agreement are: provide technical support to the MSPP for the preparation of routine manuals, standardization of care and operational protocols to be used in emergency departments; promote capacity building and provide technical support for MSPP managers, health professionals and technicians; support the expansion and consolidation of the Community Health Model (ASCP / ESF / RISS) to ensure continuity of health care and community participation.

- Outputs:

Under the output 1. Perform diagnostic assessment of the management model of urgency and emergency services in Haiti, the following activities were completed in 2017 and 2018:

1.1.Map the public health services that make up the urgency and emergency health services network in Haiti, at the community, reference community, and department levels.

1.2. Map work processes in the services involved that make up the in urgency and emergency health care network in Haiti.

1.3. Map the flow among the services that make up the urgency and emergency health care network in Haiti.

1.4. Identify the epidemiological profile of urgencies and emergencies in Haiti and the profile of references of the major treatment centers.

Activities foreseen in Output 2 - Provide technical support to the Ministry of Public Health and Population (MSPP) in defining the organizational structure, organizational chart, professional profile, and positions regarding the Management of Urgencies and Emergencies in the country” were conducted by GOH itself and will not be necessary under the scope of this Project anymore.

Referring to Output 3 “Provide technical support to the development of optimal flow of emergency care procedures, referencing and counter referencing, and the preparation of an Improvements Action Plan”, the GoB presented a proposal of implementing the Lean methodology in the HCRs in Haiti. The Lean Project in emergencies is a Brazilian Ministry of Health Project implemented by Hospital Sírio Libanês, to reduce overcrowding in emergencies of public and philanthropic hospitals. A procurement process was conducted, but due to the pandemic of the new coronavirus and the necessity to implement the contract in loco, the contract was cancelled. The completion of this output was also foreseen in the Agreement signed with OPAS and was achieved through capacity building and trainings activities.

Outputs 4, 5 and 6 was implemented through the Agreement with PAHO/WHO, signed in 2019. The key achievements under the 3 expected outcomes are:

- Improved management of three hospitals in Haiti through capacity-building: Up-to-date National Diagnostics and Therapeutics Guide; Medical Directors, Administrators and Head Nurses of the three hospitals targeted by the project trained in Management of Health institutions during crisis situations; Haiti Node on the Virtual Campus of Public Health of PAHO/WHO established as a platform for the implementation of regional courses translated to French and adapted to the Haitian context. Currently, the regional course on Maternal and Perinatal Death Surveillance and Response (MPDSR) of the Latin American Perinatal Center (CLAP) is translated to French and available in the Haiti Node.

- Integrated health services established around the three hospitals through strengthened governance: Community health model expanded; Draft theoretical framework of the Unité d’Arrondissement de Santé (UAS) developed; Equipment donated to UAS and hôpitaux communautaires de référence (HCR) targeted by the project to ensure the continuity of health services at the first level of care.

- Improved individual emergency care: Medical regulation tool developed; Surveillance and alert and response systems for epidemic-prone diseases strengthened; Public health personnel trained on emergency case management; National Plan for the Response to Exceptional Sanitary Situations developed and implemented, as well as department-level versions; Elaboration, training, and training platform for Plans blancs (Mass Casualty plans).

Please see the final report of the Agreement with PAHO/WHO on Annex 1.

Under Output 7 were organized missions from the Brazilian team to Haiti with a view of monitoring the implementation of the Project. The last mission was held in January 2020 (please note travel report on Annex 2) and further visits were suspended due to covid19 pandemic. Nevertheless, monthly meetings were organized throughout 2020 with the counterparts of the project: GoB, GoH, ABC, UNOPS, PAHO/WHO and UNDP Brazil.

Outputs 8, 9 and 10 are referred to the Agreement signed with UNOPS:

8. Support access to the provision of health care in urgencies and emergencies through the physical structuring of services and the technology park of the hospitals covered.

9. Support the operationalization on, and the follow-up of, the three HCRs (Bon Repos, Beudet and Carrefour) and the Haitian Rehabilitation Institute;

10. Transfer the total management of the HCRs and of the IHR to the MSPP.

The Agreement signed with UNOPS had the objective to implement a project in which both transactional and capacity building activities related to the maintenance and operation of the HCRs and the HRI are included. In collaboration with the MSPP, UNDP Brazil and the MoH, four levels of activities have been identified in order to continue operations and guarantee the sustainability of the project investments: (1) to optimize the operations of these health facilities and assets, and (2) to establish sustainable capacities within the MSPP maintenance units, (3) to guarantee the offer of medical services to the local population and (4) to implement a progressive handover plan so that the three hospitals and IHR become under the MSPP full control and financial support.

Please find in Annex 3 the lasts Quarterly Progress Report from the Agreement signed with UNOPS.

- Describe any delays in implementation, challenges, lessons learned & best practices:

Projects’ Initial Revision was signed on August 3rd, 2017. Implementation started right after the signature of the Prodoc and was on time with schedule. Nevertheless, a delay in the construction of the administrative buildings in the HCR of Bon Repos and Carrefour conducted by UNOPS was identified. Political turmoil in the country in 2019 also led to a delay in the implementation of field activities conducted by PAHO/WHO. Because of that, an extension of the project duration from October 2020 to December 2020 was required to complete actions foreseen in the Agreements signed with the referred agencies.

In March 2020, the global community was taken aback by the covid-19 pandemic. Immediately after the identification of community transmission of the virus in Haiti, the Project Steering Committee began to reprogram activities previously agreed with partners, eliminating actions that would imply risk to the population, to service providers and partners. Additionally, it directed efforts and resources to the acquisition of individual protection equipment and training focused on combating and controlling the new corona virus.

In direct dialogue with the GoH, the Steering Committee began the negotiations with UNOPS and PAHO/WHO to reprogram project's activities to address national emergencies to combat the pandemic. At the end a total amount of USD 2,4 million has been reprogrammed to include activities such as:

  - Strengthening the coordination capacity at national and departmental levels to support the response to covid-19.

  - Purchase of personal protective equipment (PPE) and medical equipment.

  - Adaptation of the therapeutic diagnostic guide to COVID-19 and the training on the revised guide.

  - Staff training at UAS and community level.

  - Covid-19 monitoring.

  - Personnel training on case management, prevention and infection control.

  - Strengthening medical regulatory capacity to guide quickly.

  - Technical evaluation of potential Covid-19 treatment centers. The technical assistance also includes the preparation of technical specifications, as well as the technical evaluation of the offers received by the Ministry (the UNOPS team is part of the MSPP Crisis Management Group to coordinate and harmonize all efforts to combat covid-19).

  - Market research / sourcing and support in identifying potential suppliers which can provide Personal Protective Equipment / Oxygen Concentrators, cylinders, accessories.

In view of that, new Amendments to the Agreements with UNOPS and PAHO were issued:

- Amendment 2 with PAHO-WHO signed in May 2020 with the objective of reprogramming activities to combat covid-19 in Haiti. Please see Annex 4.

- Amendment 4 with UNOPS signed in June 2020 with the objective of increase budget total amount in USD 200,000 and reprogram activities before aimed at the reform of La Paix Hospital to combat covid-19. Annex 5.

Despite the reprogramming of the Project's activities, some ongoing commitments had to be maintained, being severely impacted by exceptional circumstances related to the advancement of the covid-19 pandemic in Haiti. The outbreak of the pandemic caused a considerable delay in the construction of the administrative centers at the Bon Repos and Carrefour hospitals, which were commissioned under the Agreement signed with UNOPS in November 2019 and initially scheduled to end in December 2020.

Therefore, it will be necessary to extend the project's deadline to complete these works in Bon Repos and Carrefour. Furthermore, the extension is required to ensure the continuation of provisions relating to the closure of the Project and the formal transfer of the HCRs and the IHR to the Haitian Government. This was a challenge for 2020 but couldn’t be implemented due the delays caused by covid19 pandemic.

In view of that, on October 2020 the Steering Committee sent a correspondence to the Haitian Reconstruction Fund, represented by the Haitian Finance Minister, requesting the extension of the Fund and also of the project (see Annex 6).

Since then, a series of meetings and exchanges were held between the parts and the donors to decide the new arrangements needed for the Fund extension. The updated situation of the negotiations with the 18 signatory countries of the Fund are:

- 13 have signed the document "Amendment to the Administration Agreement";

- 3 signed a document to shut down the Fund (including Sweden, which had already withdrawn from the FRH in 2017); and

- 2 are concluding their internal procedures relating to the issue.

It is still necessary to finalize the internal procedures of the 2 countries pending response to formalize the extension of the Fund and only after this stage it will be possible to submit a project revision and extend the duration of the project. Meanwhile, UNDP Brazil is preparing for the continuity of the project and holds permanent contact with the members of project’s Steering Committee in order to approve a workplan for 2021 (activities and disbursements were suspended at the end of 2020).

In view of the delay in the constructions of the administrative buildings in Bon Repos and Carrefour, UNOPS Haiti presented an amendment proposal, which is being analyzed by the Steering Committee. (Annex 7). At this time UNDP Brazil is planning a meeting with the Steering Committee to follow up the negotiations on the extension and to approve UNOPS proposal.

- Qualitative assessment:

Dialogue and transfer of knowledge between MSPP, GoB and UNDP teams were essential to the positive results achieved and to surpass the pandemic period. The risk matrix was brutally impacted by the unexpected crisis and had to be updated. A project review will be submitted for approval as soon as the Fund is extended and, so far, there is no Programmatic revision foreseen.

Taking into consideration the challenges faced in 2020, the results achieved are very satisfactory. The reprogramming of activities was conducted on time and with the cooperation of the parts.