MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2019

| Programme Title & Project Number |  |  | Country, Locality(s), Priority Area(s) / Strategic Results |  |
| --- | --- | --- | --- | --- |
| - Programme Title: Support to Technical and Vocational Education and Training in Haiti through the Establishment of a Vocational Training Center and Related Institutional Strengthening - Programme Number: BRA/16/004 00095226 - MPTF Office Project Reference Number: UNDG/HRF-13 Vocational Training |  |  | Country/Region: Brazil/LA |  |
|  |  |  | UNDAF 4: South-South Cooperation in the Context of Sustainable Development and Eradication of Poverty. Country Programme Document/CPD: 4.1. Knowledge management mechanisms strengthened; 4.2 Expanding South-South cooperation agenda by including broad, planned and complementary themes. |  |
| Participating Organization(s) |  |  | Implementing Partners |  |
| - UNDP Brazil |  |  | - UNDP Haiti |  |
| Programme/Project Cost (US$) |  |  | Programme Duration |  |
| Total approved budget as per project document: 17,000,000.00 MPTF /JP Contribution: - UNDP Brazil US$ 16,830,000.00 |  |  | Overall Duration; 4 ½ years |  |
| Agency Contribution:N/A) |  |  | Start Date: 13th July 2016 |  |
| Government Contribution:N/A |  |  | Original End Date 31st December 2019 |  |
| Other Contributions (donors): N/A |  |  | Current End date: 31st December 2020 |  |
| TOTAL: US$ 16,830,000.00 |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  |  | Report Submitted By |  |
| Assessment/Review - 1st Substantive Revision attached X Yes No Date: 24/05/2018 Mid-Term Evaluation Report – N/A Yes No Date: dd.mm.yyyy |  |  | - Name: Luciana Brant / Cristiano Prado - Title: Project Manager / Programme Analyst - Participating Organization (Lead): UNDP Brazil - Email address: Luciana.brant@undp.org / Cristiano.prado@undp.org |  |

# NARRATIVE REPORT

# EXECUTIVE SUMMARY

- The terrible earthquake of January 12, 2010, which struck Haiti, had greatly affected the Haitian education system, particularly the vocational training sector. However, this devastating event served as a pretext for the Government of the Republic to begin the Re-foundation of the Educational System. The Vocational Training sector has been identified  as a major area of intervention and the project “Support to Technical and Vocational Education and Training in Haiti through the Establishment of a Vocational Training Center and Related Institutional Strengthening” is part of this dynamic and responds to the need to promote the development of public provision of technical and vocational training, and the qualification of the workforce, with a view to generating employment and social promotion for young Haitians.

- The project rests on four pillars of intervention: (i) building (initially) one vocational training center (Les Cayes) (ii) performing institutional strengthening actions to support Institut National de Formation Professionnelle et Technique (INFP); (iii) offering a training and educational program for the target population, supported by a set of community outreach activities carried out by the National Services for Industrial Learning (SENAI), from Brazil, with the support of INFP and other partner entities with a view to raise boys’ and girls’ interest to pursue technical and vocational education; and (iv) project management, monitoring and evaluation.

- As informed by the previously report this project was designed, elaborated and signed under the government of President Martelly in July 2016. At the end of May and the beginning of June 2017, the first project mission was held in PAP/Haiti with a new government established.

- During the first mission in Haiti, held in May 2017, the GoH, through its new director of the INFP, requested the revision of the project to increase the number of Vocational Training Centers from one to three. GoH also indicated the possible sites for the VTC’s installation: Les Cayes, St. Marc and Fort Liberté. After the 1st mission, four Steering Committee meetings were carried out to negotiate the construction of the three VTC, instead of one, leading to budget and workplan relocation, changing meaningfully the project and the budget allocation.

- In April 2018, in a bilateral meeting between GoB and GoH, a final agreement on the budget was reached to implement both the hard component (construction of three centers / equipment) and the soft component (methodology and training to teachers and to the general public). As a result, a 1st substantive revision of this project was designed by UNDP and approved by all partners and the project board (Institut National de Formation Professionnelle/INFP, Brazilian Agency Cooperation/ABC, UNDP Brazil, UNDP Haiti and SENAI) in May 2018.

- The strategy was, therefore, to build the three centers in Haiti and, during the final period of construction, to train Haitian teachers, allowing them to dominate the methodology and knowledge.

- After this decision, and despite the best efforts to move on, project faced several challenges that prevented its advance as expected, such as: political instability in Haiti, challenges on the chosen terrain to build the first VTC in Les Cayes, such as additional engineering studies were needed because of flood risk, the legal property title was obtained by INFP only in 2020, delays on the bidding process for Les Cayes ( first bidding on September 2018 was unsuccessful, the second was launched on Feb 2019 and contract was signed in the end of year) and the delay on Les Cayes construction because of turmoils/riots. Considering these difficulties, and the lack of time for bidding and constructing the 2nd and 3rd center, the bidding process for those centers were not yet released. Finally, in the end of first quarter of 2020, the unprecedent and unexpected impact of COVID 19 hit hard Brazil and Haiti, delaying even more the construction progress with the corollary of hitting heavily the soft component implementation plan.

- Given all these obstacles in the field, just one of the three VTCs is currently under construction. Works are around 20 to 25% by as of the second half of  May-2020.  According to the work  plan and contract,  the forecast was to have the Les Cayes’ VTC  ready by June 2020, although recent local turmoil led us to believe that September would be more feasible. But that was before COVID 19, and now as informed by UNDP Haiti the country is paralyzed and it is not possible to foresee by now when the VTC will be ready.

- Considering all the actual and planned expenses, resources available on the hard component would be enough to build a second center and, considering all the project budget (hard + soft), there is enough resources to build the three centers. Nonetheless, there is not enough time left to build the other two centers. According to UNDP Haiti, if bidding process is released in the next months, in a regular non-COVID scenario, Saint Marc could be ready by July 2021, and Fort Liberté by September 2021.

- The soft component (training) strategy was designed to be implemented after the VTCs were built and fully equipped. Also, for the soft component implementation, the professional teams (managers and teachers) of the VTCs had to be identified and ready to receive the training sessions at new facilities. The construction delay prevented the implementation of this strategy, and other options are now being considered for review of the Steering committee.  Examples include:

  - Buying mobile training centers to use in Haiti, as alternative to the 2 VTCs .

  - Develop online training courses for the Hatian professional teams using other local facilities in Haiti that are available and meet the technical requirements in terms of internet connection and equipment.

- A Steering Committee meeting is expected to be held in June/2020 to discuss the different possibilities aiming to develop alternatives for the project implementation, considering the proximity of its current end date of December 31/2020.

# Purpose

- The project aims at supporting the efforts by the Haitian government to rebuild the country in a way that addresses longstanding, structural challenges that have delayed social and economic development for the last past years by contributing to the employability of the country’s population, particularly the youth. Expected impact will include income generation through employment and self-employment.  The project will also enable an expansion of the private sector by increasing the supply of qualified labor, thus contributing to a reduction of poverty over the longer term.

- The project addresses the imperative to pursue the expansion of technical and vocational education, job generation and social promotion.

# Results

- Narrative reporting on results:

The project has three operational components. UNDP-Haiti is responsible of the "Hard component" of the project which concerns the construction of the three vocational centers and the provision of equipment for the Vocational school of Les Cayes:

- Outputs 1.3 Vocational training center built or upgrade to offer initially vocational training center;

- Outputs 1.4 Vocational training center equipped with tools, machinery and furniture for development of vocational training courses; and

- Outputs 4.1 Project managed, monitored and evaluated.

Initially the project aimed to build a vocational school in the city of Les Cayes, but following the request of INFP, approved by the Steering Committee, the number of VTC increased to three as follows:

- Les Cayes (4500 m2) with the following sectors: metal mechanics, information technology, civil construction, refrigeration, automotive

- Fort Liberté (1280 m2) : Civil construction, refrigeration, information technology

- St-Marc (1080 m2): Information technology and civil construction.

- Outcomes:

Outcome 1 - Vocational training centers establish with a capacity to train about 3000 students.

ACTIVITIES CARRIED OUT ON THE BASIS OF THE EXPECTED RESULTS FOR THE PERIOD

Preliminary studies were completed during the period:

1- Call for tenders for the construction of the vocational school in Les Cayes,

2- Call for tenders for the supervision of school’s construction in Les Cayes,

3- Awarding of the construction contract to the firm Emco,

4- Awarding of the supervision contract to the firm WE Architect,

5- Issuance of start order and start of construction work in June 2019,

6- Follow-up of the works by the project team with missions to Les Cayes on average twice a month,

7- Preliminary Studies for the construction of the VTC in Saint-Marc and Fort-Liberte were completed.

8- Recruitment of a legal expert in order to regularize the title deeds of the construction site of VTC les Cayes which were not in the name of the INFP or the Ministry of Education in Haiti. The title deed is now regularized, according to the information provided by the Haitian Government and UNDP Haiti.

The situation on December 2019 was as follows:

- 16% of the resources were used (roughly US$ 2.7 million out of US$ 16.8 million).

- Just one of the three VTCs is currently under construction. As of May/2020 works are around 20 to 25%.  First forecast was to have it ready by June 2020, but due to turmoil/riots the conclusion date was more likely to shift to September2020, not considering the Covid-19 impact.

- The bidding processes for the 2nd and 3rd VTC were not yet released, considering lack of remaining time to build them.

- Equipment for Les Cayes were not procured yet, as the construction must advance in order to the center be ready to receive the equipment.

Outcome 2 - INFP institutionally strengthened focusing on further developing its capacity to fulfill its institutional mandate to promote technical and occupational education in Haiti.

02 (two) Outputs and some activities are expected to be carried out after the Vocational Training Centers/VTCs are delivered to the Government of Haiti, i.e., after construction and after equipping them. These outputs aim to qualify INFP trainers to work into the VTCs, and to prepare INFP’s management team to work into the VTCs.

Outcome 3 - Training programs offered for the general population on occupations with particular focus on youth and high employability and/or self-employment potentials.

03 (three) Outputs and some activities were previously expected to be carried out after the Vocational Training Centers/VTCs are delivered to the Government of Haiti, i.e., after construction and after equipping them. These outputs apply to the development of teaching resources (materials for classes), vocational training courses in the selected areas developed at VTCs and actions to promote Gender Equity, environmental sustainability and entrepreneurship. Nonetheless, considering the delay of the VTC building, the proximity of the project end date, and the Covid19 pandemic, alternatives to implement the training programs are being discussed and shall be analyzed in the next Steering Committee meeting.

Outcome 4 - Project adequately managed, monitored and evaluated.

01 (one) Output carried out which refers to management activities of this project both from UNDP Brazil and UNDP Haiti staff and project personnel. During 2019, project was dully monitored, and best efforts were made to accelerate its development, but the sequence of challenges above-mentioned prevented the project to perform as expected along that year.

- Describe any delays in implementation, challenges, lessons learned & best practices:

A negotiation began in the first mission to Haiti in 2017 to review the hard component of the project (construction and supply of equipment for the Vocational Training Center) and the soft component (SENAI professional training methodology), and in May 2018 the 1st substantive revision of BRA/16/004 was approved. Two INFP and UNDP Haiti missions to Brazil were held, in addition to four meetings of the Project Steering Committee, to negotiate the substantive revision. In this sense, the negotiations to change from one to three centers – and continuous request by the GoH to keep renegotiating the financial terms and the balance between the hard and soft component - were relevant reasons for the initial delays in the execution of the project.

Despite the best efforts to move on, after the first substantive revision,  the project faced several challenges that prevented its advancement as planned, such as: political instability in Haiti, challenges on the chosen terrain to build the first VTC, additional engineering studies were needed because of flood risk, delays on the bidding process for Les Cayes (first bidding on September 2018 was unsuccessful , the second was launched on Feb 2019 and contract signed in the end of year) and lack of documentation of land ownership. Because of these challenges, the building of the 1st VTC is not ready yet, which consequently resulted in in delays of the soft component implementation. Additionally, the bidding process for the 2nd and 3rd center was yet not initiated due to lack of time for bidding and construction under the project duration. And finally, the rise of the Covid19 pandemic brought new challenges to the project, not only causing further delays on the construction of Les Cayes, but also forcing the project to develop creative alternatives to implement both the hard and soft components, such as the mobile centers and “on line training. It is important to notice that these strategies might also face new challenges, considering the need and availability of adequate infrastructure (such as broadband, energy, computers) and soft skills (computer knowledge) among Haitian people.

As lessons learned, it is important to highlight the risk of continuous renegotiation of the objectives and of the program budget, as it prevents the implementation to be delivered done on time and properly; and the need to have a conservative analysis of the keys issues such as timing and capabilities of implementing the project under a challenging environment, availability of resources and inputs needed for the project in that environment and the risks of turmoil’s and political challenges.

- Qualitative assessment: Provide a qualitative assessment of the level of overall achievement of the Programme. Highlight key partnerships and explain how such relationships impacted on the achievement of results. Explain cross-cutting issues pertinent to the results being reported on. For Joint Programmes, highlight how UN coordination has been affected in support of achievement of results.

Although the best efforts were made, several challenges prevent the project to perform as expected within the timeframe. It is important to notice that all the key partners   - UNDP Brazil, UNDP Brazil,  ABC – Brazilian Agency of Cooperation,  SENAI, and INFP are engaged in finding alternative solutions to speed up proper implementation of the project, even under the existing challenges, considering that the financial resources are still available and that all partners are committed to reach the objectives of the project and ensure the full transfer of knowledge from Brazil to Haiti. However, that would only be possible with a project extension.

ii) Indicator Based Performance Assessment:

|  |  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- | --- |
| Outcome 1 Vocational training centers establish with a capacity train about 3000 student a year Indicator:3000 students learning Baseline:0 Planned Target: 3 |  |  |  |  |
| Output 1.3 Vocational training center built or upgrade to offer initially vocational training courses | Indicator nr.1: Administrative building build and/or upgrade Baseline:0 Planned Target:3 | 10% | During this period, the call for tenders was launched for the construction and supervision of the Vocational School of Les Cayes. Work began in June/2019. Political turbulence between September and November created a delay and at the end of the period, the progress of the works was estimated at 10%-15%. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 1.3 Vocational training center built or upgrade to offer initially vocational training courses | Indicator nr.1: # of theorical classroom build and /or upgrade Baseline:0 Planned Target:4 Indicator nr.2: # of pavilions for workshop and laboratories built and or upgrade Baseline:0 Planned Target:4 | 10% | During this period, the call for tenders was launched for the construction and supervision of the Vocational school of Les Cayes. Work began in June/2019 Political turbulence between September and November created a delay and at the end of the period, the progress of the works was estimated at 10%-15%. | Project reports, monthly reports from the construction supervision firm, pictures. |
|  |  | 10% | During this period, the call for tenders was launched for the construction and supervision of the Vocational school of Les Cayes. Work began in June/2019. Political turbulence between September and November created a delay and at the end of the period, the progress of the works was estimated at 10%-15%. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 1.4 Vocational training center equipped with tools machinery and furniture for development of vocational training courses | Indicator nr.1: # of sets of tools(one for each technological area) purchased Baseline:0 Planned Target:8 | 0% | During the 3rd steering committee meeting held in July 2018 it was decided that this output could not be envisaged since the construction had not started. This activity can only be envisaged as designed when the construction of the VTC of Les Cayes reaches at least 40% of its execution – This percentage shall be reached in mid-2020 and then the call for tenders for the purchase of goods/equipment will be issued. | Project reports, monthly reports from the construction supervision firm, pictures. |
|  | Indicator nr.2: # of equipment for workshops and laboratories purchased and installed Baseline:0 Planned Target:8 Indicator nr.3: # of rooms furnished to administrative areas and lecture Baseline:0 Planned Target:20 | 0% | During the 3rd steering committee meeting held in July 2018 it was decided that this output could not be envisaged since the construction had not started. This activity can only be envisaged as designed when the construction of the VTC of Les Cayes reaches at least 40% of its execution – This percentage shall be reached in mid-2020 and then the call for tenders for the purchase of goods/equipment will be issued. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 2.1 - INFP trainers qualified to work in Vocational Training Centre and able to disseminate new knowledge | Indicator: nr.1: # of INFP trainers qualified teaching practice, disaggregated by gender. Baseline: 0 Planned target: 50 Indicator nr.2: # of INFP trainers trained to practice technique, disaggregated by gender. Baseline: 0 Planned Target: 32 | 0% | As the construction of the VTC delayed, the training could not start – it was planned to start when the construction of the VTC of Les Cayes reaches near 100% of its execution. Alternative methodologies, such as online learning, will analyzed by the next SC to be executed in parallel to the construction of Les Cayes to speed up implementation of component 2. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 2.2 - INFP technicians trained to identify demands, job profiles, curriculum design and certification | Indicator nr.1: # of INFP technicians trained to identify demands and develop curricula, disaggregated by gender. Baseline: 0 Planned target: 10 | 0% | As the construction of the VTC delayed, the training could not start – it was planned to start when the construction of the VTC of Les Cayes reaches near 100% of its execution Alternative methodologies, such as online learning, will analyzed by the next SC to be executed in parallel to the construction of Les Cayes to speed up implementation of component 2. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 2.3 - Managers and administrative support staff of INFP prepared to act in Vocational Training Centre | Indicator nr.1: # of INFP technicians trained in office practices of vocational training centers, disaggregated by gender. Baseline: 0 Planned target: 6 Indicator nr.2: # of INFP managers trained in vocational training centers management, disaggregated by gender. Baseline: 0 Planned target: 6 | 0% | As the construction of the VTC delayed, the training could not start – it was planned to start when the construction of the VTC of Les Cayes reaches near 100% of its execution Alternative methodologies, such as online learning, will analyzed by the next SC to be executed in parallel to the construction of Les Cayes to speed up implementation of component 2. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 3.1 - Teaching resources (printed) of selected areas (R2.1) developed for application in professional training courses at HBVTC | Indicator nr.1: # of booklets developed for courses in the HBVTC. Baseline: 0 Planned target: 24 | 0% | As the construction of the Les Cayes VTC delayed, and the bidding for the other two VTCs has not yet been launched, UNDP Brazil and SENAI have been adjusting the work plan to produce and deliver the teaching resources accordingly. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 3.2 -Vocational training courses in the selected areas (R2.1) developed at HBVTC | Indicator nr.1: # of courses conducted in the HBVTC. Baseline: 0 Planned target: 24 | 0% | Activities have not started as VTCs are not ready. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 3.3 -Actions to promote Gender Equity, Environmental Sustainability and Entrepreneurship developed | Indicator nr.1: # of promotion actions for gender equity held. Baseline: 0 Planned target: 01 Indicator nr.2: # of promotion actions for environmental sustainability held. Baseline: 0 Planned target: 02 Indicator nr.3: # of promotion actions for entrepreneurship held. Baseline: 0 Planned target: 02 | 0% | As the project and the build of the VTC delayed, these actions didn’t start yet. | Project reports, monthly reports from the construction supervision firm, pictures. |
| Output 4.1 - Project managed, monitored and evaluated | Indicator nr.1: # of administrative technicians hired to support the project. Baseline: 0 Planned target: 02 Indicator nr.2: # of technical coordinator to implement the project. Baseline: 0 Planned target: 01 Indicator nr.3: # of senior coordinator hired to implement the project. Baseline: 0 Planned target: 01 Indicator nr.4: # of administrative technicians hired to support the project. Baseline: 0 Planned target: 02 Indicator nr.5: # of project analysts hired for monitoring and evaluation. Baseline: 0 Planned target: 01 Indicator nr.6: Carry out quarterly missions to monitoring and mid-term evaluation. Baseline: 0 Planned target: 4 Indicator nr. 7: Auditing Exercises. Baseline: 0 Planned target: 1 Indicator nr. 8: Carry out final evaluation. Baseline:0 Planned target: 1 | 0%. 0 technicians were contracted for SENAI to general and operational project’s support at PAP/Haiti. 100%. 01 project manager was hired for UNDP Haiti to manage the project and liaison with the Counterparts. 0%. 0 team contracted to support the Brazilian Embassy at PAP/Haiti 100%. 02 project’s analysts were hired for ABC to monitor and co-coordinate the project. 0%. 0 project analyst was hired to monitoring and evaluating the project. 0 % missions occurred at 2019 N/A to 2019 N/A to 2019 | No missions were held in 2019 because of the turmoil’s in Haiti. Yet, continuous exchanges were maintained among all project members and partners, aiming to map and overcome project challenges | Project reports, monthly reports from the construction supervision firm, pictures, exchanges of emails among UNDP Brazil, UNDP Haiti, SENAI, ABC and INFP. |

Problem / Challenge faced: The project faced several challenges in 2019 and now in 2020, as above-mentioned. Among them, one can highlight the unexpected delay to conclude the bidding process for Les Cayes’ VTC, together with land title problems, geotechnical challenges and delays in the construction works because of the turmoil’s in Haiti. Indeed, a relevant obstacle was the political instability of the country: from September to November 2019 the activities were practically paralyzed and to up to December 2019 the progress rate of the Les Cayes construction was 10 - 15 %. Delays are therefore accumulated and prevent the achievement of the project objectives. On top of that, the Covid19 pandemic brought new challenges to project implementation, as it is forcing further delays on Les Cayes’ construction and making the strategy of the soft component (face-to-face training) unfeasible in the short term. In this sense, alternatives will be discussed by the Steering Committee on the next meeting that is expected to be held in June. It is important to notice that, considering all the actual and planned expenses, resources available on the hard component would be enough to build a second center and, considering all the project budget (hard + soft), there is enough resources to build the three centers. Nonetheless, there is not enough time left to build the other two centers, as project is expected to be operationally closed in December 2020. According to UNDP Haiti, with a bidding process being released in the next months, in a regular scenario Saint Marc could be ready by July 2021 and Fort Liberté by September 2021. That said, even with the best efforts, the project has not reached its objectives yet for reasons that were beyond control. Considering the proximity of project end date, the observed delays and the pandemic, the chances of reaching project’s objectives by the end of year are really low. If more time was available for project implementation, the balance amount would be enough to execute project outputs/activities to achieve project goals. Programme Interventions: How was the problem or challenged addressed through the Programme interventions? Result: Several meetings and discussions were held, aiming to find alternatives to improve project execution. Examples include the possibility of buying mobile training centers as alternative to the 2 VTC, and to develop online training courses for Haitian professional teams using local facilities in Haiti. Nonetheless, availability of time for project execution is now the major challenge to implement pending outputs/activities, and these issues will be discussed in the next SC meeting planned to happen in June 2020. Lessons Learned: What did you (and/or other partners) learn from this situation that has helped inform and/or improve Programme (or other) interventions? An important learning is to try to avoid design and initiate a project during a transitional government. In addition, it is important to be extreme conservative and cautious– both in term of budget and timing - when considering the political and social cohesion risk. Another lesson learned is the importance of ensuring with all partners, that all legal documents are ready and that the Government have the land property, as it can delay the works and the project. Finally, the importance of shielding the project from continuous renegotiation and redesign, as it will - undoubtedly - affect the project execution.

III.	Other Assessments or Evaluations (if applicable)

• It is important to analyze the possibility of a new project extension, on an exceptional basis, that would allow its orderly and complete conclusion. Indeed, there are enough funds for its completion and both the Brazilian and the Haitian Governments support project implementation.  The Covid19 pandemic brought new challenges that added to previous obstacles/difficulties, pushing the project to new delays and in need of extra time for full execution. Without the extension, the project will end, even with the best efforts, without reaching fully its objectives.

IV. Programmatic Revisions: See below the summary of the 1st substantive revision of this project as document attached:

V. 	Resources (Optional)

Annex 1 – 1st Substantive Revision including the 1st Steering Committee minutes and 2nd Steering Committee minutes;

Annex 2 – 3rd Steering Committee minutes

Annex 3 – 4th Steering Committee minutes

1ST BUDGET REVISION – SUBSTANTIVE REVISION

Les Cayes Works – Jan / 2020

Finished reinforcement awaiting the pouring of concrete

Finished reinforcement awaiting the pouring of concrete

Putting in place concrete of cleanliness and starting of the reinforcement

Finished reinforcement awaiting the pouring of concrete

Second layer of backfill in classrooms awaiting compaction test by the building laboratory (LNBTP)

Les Cayes Works – Feb/2020

Les Cayes Works – Feb/2020

Les Cayes Works – Feb/2020

Les Cayes Works – Feb/2020

Les Cayes Works – Feb/2020

Les Cayes Works – Feb/2020

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.